## DASHBOARD
NO | ITEMS | QTY | Unit | Unit Price | Total Price | Purchasement Date | Delivery Date | Delivery Type | Additional Insurance Requirement | Lojistic Requirement | Notes
1 | PV MODULE & CONNECTOR | [6 empty] | On-site
2 | SOLAR CABLE | [6 empty] | EXW
3 | INVERTER | [6 empty] | CIF
4 | CONSTRUCTION MATERIAL (TRACKER) | [6 empty] | ?
5 | CIVIL&ELECTRICAL WORKS
6 | MV EQUIPMENTS FOR SPP
7 | LV PANELS
8 | CABLES
9 | GRID CONNECTION (TURN-KEY)
10 | FENCES
11 | EARTHING & LIGHTINING EQUIPMENTS
12 | FIRE EXTINGUISHING SYSTEM
13 | LOGERG & GUARDIAN 3.0 & DRON
14 | CCTV (AVAILABLE TO LOGERG)
15 | ELECTRICAL EQUIPMENTS
16 | VILLA (CONTAINERIZED) & SITE DEPOT
17 | LANDSCAPING WORKS
18 | MANAGEMENT EXPENSES
19 | CEMENT, SAND AND OTHER CIVIL GOODS
20 | MAP ENGINEERING
21 | CONSULTANTS (PWC, CUSTOM CONS., PV MODULE INSPECTOR. COMM. SUPERVISOR)
22 | TAXES AND FEES FOR CONSTRUCTION AND CUSTOM DUTIES
24 | ALL RISK INSURANCE
25 | LOGISTICS (REGIONAL COMPANY)
26 | CUSTOMS WAREHOUSE
27 | OTHERS (ADDITIONAL INSURANCE, OTHER SITE NEEDS)

## Definitions
NO | ITEMS | PURCH. TYPE | MADE IN | SUPPLIER | PRODUCER (BRAND) | CUSTOMS REQ. | PA | PM | PD | NOTES
1 | PV MODULE & CONNECTOR | GB | PRC | JINKO | JINKO | YES
2 | SOLAR CABLE | GB | TR | EGE KABLO | EGE KABLO | YES
3 | INVERTER | GB | PRC | HUAWEI | HUAWEI | YES
4 | CONSTRUCTION MATERIAL (TRACKER) | GB | TR OR PRC | SCHLETTER | SCHLETTER | YES
5 | CIVIL&ELECTRICAL WORKS | SL | EU | EASTERN EUROPEAN COMPANIES | EASTERN EUROPEAN COMPANIES | NO
6 | MV EQUIPMENTS FOR SPP | GB | TR | ERGINER | ORMAZABAL, RTS PREFABRIC, ELTAŞ | ? |  |  |  | İHRAÇ KAYITLI ¦ İTALYAN ŞİRKET DE ARAYALIM
7 | LV PANELS | GB | TR | TEKPAN | TEKPAN | YES
8 | CABLES | GS | TR | ÖZNUR (ERGİNER) | ÖZNUR PYRISMIAN(COM. CABLE) | YES |  |  |  | İHRAÇ KAYITLI
9 | GRID CONNECTION (TURN-KEY) | CB | - | ITALIAN COMPANY | ITALIAN COMPANY |  |  |  |  | MV CABLES EXCLUDED ¦ MV SWITCHGEARS INCLUDED ¦ TERNA&ENEL SCADA INCLUDED
10 | FENCES | GS (CS) | ITA OR TR | ITALIAN COMPANY | ITALIAN COMPANY
11 | EARTHING & LIGHTINING EQUIPMENTS | GS | TR | ERGINER | RADSAN | YES |  |  |  | İHRAÇ KAYITLI
12 | FIRE EXTINGUISHING SYSTEM | CS | ITA | ITALIAN COMPANY | ITALIAN COMPANY
13 | LOGERG & GUARDIAN 3.0 & DRON | LIST | TR | ERGINER | EU COMPANIES | ? |  |  |  | DIŞ TİCARET UZMANI İLE GÖRÜŞÜLECEK.
14 | CCTV (AVAILABLE TO LOGERG) | CS | TR | ERGINER | ? | ? |  |  |  | DİREKT ALINABİLECEK FİRMALAR ARAŞTIRILACAK.
15 | ELECTRICAL EQUIPMENTS | GS | TR | ITALIAN COMPANY | ITALIAN COMPANY | NO |  |  |  | BAŞLIK, PABUÇ, MAKARON (ETC)
16 | VILLA (CONTAINERIZED) & SITE DEPOT | GB | TR | ERGINER | ERGINER | YES
17 | LANDSCAPING WORKS | CB | ITA | ITALIAN COMPANY | ITALIAN COMPANY | NO
18 | MANAGEMENT EXPENSES | LIST | ITA | SPV | SPV | NO
19 | CEMENT, SAND AND OTHER CIVIL GOODS | GS | ITA | ITALIAN COMPANY | ITALIAN COMPANY | NO
20 | MAP ENGINEERING | SC | ITA | ITALIAN COMPANY | ITALIAN COMPANY | NO
21 | CONSULTANTS (PWC, CUSTOM CONS., PV MODULE INSPECTOR. COMM. SUPERVISOR) | LIST | - | INTERNATIONAL COMPANIES | INTERNATIONAL COMPANIES | NO
22 | TAXES AND FEES FOR CONSTRUCTION AND CUSTOM DUTIES | LIST | ITA | SPV | SPV | NO
24 | ALL RISK INSURANCE | SC | ITA | PWC | - | NO
25 | LOGISTICS (REGIONAL COMPANY) | SL | ITA
26 | INTERNATIONAL LOGISTICS | SL | EU
26 | CUSTOMS WAREHOUSE | SC | ITA
27 | OTHERS (ADDITIONAL INSURANCE, OTHER SITE NEEDS) | LIST | ITA | ITALIAN COMPANY | ITALIAN COMPANY | NO

## Subdefinitions
AFMB: ALIŞ FATURALARI MAL BÜYÜK | GB | GOODS BIG
AFMK: ALIŞ FATURALARI MAL KÜÇÜK | GS | GOODS SMALL
AFYB: ALIŞ FATURALARI YAPIM BÜYÜK | CB | CONSTRUCTION BIG
AFYK: ALIŞ FATURALARI YAPIM KÜÇÜK | CS | CONSTRUCTION SMALL
AFHİ: ALIŞ FATURALARI HİZMET İŞÇİLİK | SL | SERVICE LABOUR
AFHD: ALIŞ FATURALARI HİZMET DANIŞMANLIK | SC | SERVICE CONSULTANCY

## GB
Task Name | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
GB INSTRUCTIONS
Please define the procurement, enter the relevant date and assign a PM for this procurement. You must also give GB warning.
Please use the attached pre-prepared administrative specification as a template and update it accordingly. In addition, please prepare a technical specification for this purchase and attach it to your updated administrative specification.
Please prepare and update proposal request form. Request and gather proposals from suppliers. Archive proposals and proformas digitally.
Please prepare and update the proposal comparison chart. Submit the chart to PM.
Please check the digital archive. Submit the proposal comparison chart to PD for approval.
Please use the attached pre-prepared contract as a template and update the yellow highlighted sections accordingly. In addition, please attach the contract as ready for signing. If necessary, please consult an attorney regarding the contract.
Please review the contents of the contract and assign Project Purchasement (PO) number. Have the supplier sign the contract and submit it to PD for approval.
Please review and sign the contract
Please review the contract. Pay in advance. If necessary, add to the checklist. In addition, please inform the accounting department about the advance payment with the PO number. Upload the advance payment receipt to this row.
Please add the purchasement to the PO list.
Please organize the delivery after product is ready. If necessery, request the second paymet from MD.
Please check the contract and make the second payment due if needed. Please also notify the accounting department about this second advance payment with the Project Purchasement Number (PO No).
Please evaluate the neccessity of the FAT and also please evaluate whether the customer needed in the FAT.
Please ensure that all test documents, material identification and certificates are obtained and archived from the manufacturer, whether FAT has been done or not.
Check the attached instruction of insurances. According to the delivery type, please ensure the relevant insurance procedures is completed before transportation. Don't forget to unload and upload coverage. If any documentation is missing, please complete it and inform PM in the communicatons. |  |  |  |  | PA
Please check the insurance claim and the master insurance list, and add it to the current All-Risk-Insurance Policy if it is not added before. If you cannot add it to the All-Risk-Insurance policy, you can request two proposals for a new policy and submit them for approval of PD. In any case you need to finalize this procedure in this period. |  |  |  |  | PM
Before unloading, please ensure that the goods have been received in the correct quantity and are free of any defects. If everything is in order, please prepare delivery notes and photographs and upload the documents here according to the attached sample. In the event of goods being damaged or missing, please contact the supplier by email and phone, and contact PM and PD to request a solution. If PD or PM decide to unload these issued goods, please take detailed videos and photos before and after unloading. If you encounter this issue during or after unloading, please halt the work and follow the steps outlined above. |  |  |  |  | SM
Please check all documents recieved from SM. Please also archive all documents as hard (wet ink) and soft copies.
Please prepare the SAT (Site Acceptance Test) or Goods Delivery Record Form and sign it according to the attached sample.
Please check all documents recieved from SM. Please also archive all documents as hard(wet ink) and soft copies.
Please ensure that all documents above have been archived as hard (wet ink) and soft copies.
Please ensure that the invoice is issued correctly by supplier according to the attached sample. Additionally, please review the PO and invoice together.
Please check the PO and make the remaining payment if necessary. Additionally, please inform the accounting department about the payment with the PO number.
Please check the invoice of the exchange rate difference according to the payments made. If necessary, obtain approval from the PD to close the process accounting-wise by offsetting the payment or exchange difference invoices.
Please make final checks of the entire process and obtain confirmation from the PD that the work has been completed.
+++++++++++++++++++++

## GS
Task Name | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
GS INSTRUCTIONS | [12 empty] | 0%
Please define the procurement, enter the relevant date and assign a PM for this procurement. You must also give GS warning.
Please prepare and update proposal request form. Request and gather proposals from suppliers. Archive proposals and proformas digitally.
Please check the digital archive. Submit the proposal comparison chart to PD for approval with PM's supervision.
Please prepare a Project Purchasement (PO).
Please review the contents of the PO and assign PO number. Then, have the supplier sign the contract and submit it to PD for approval.
Please review the PO. Pay in advance. If necessary, add to the checklist. In addition, please inform the accounting department about the advance payment with the PO number. Upload the advance payment receipt to this row.
Please add the purchasement to the PO list.
Please organize the delivery after product is ready. If necessery, request the second paymet from PD.
Please check the contract and make the second payment due if needed. Please also notify the accounting department about this second advance payment with the Project Purchasement Number (PO No).
Before unloading, please ensure that the goods have been received in the correct quantity and are free of any defects. If everything is in order, please prepare delivery notes and photographs and upload the documents here according to the attached sample. In the event of goods being damaged or missing, please contact the supplier by email and phone, and contact PM and PD to request a solution. If PD or PM decide to unload these issued goods, please take detailed videos and photos before and after unloading. If you encounter this issue during or after unloading, please halt the work and follow the steps outlined above.
Please check all documents recieved from SM. Please also archive all documents as hard (wet ink) and soft copies.
Please ensure that all documents above have been archived as hard (wet ink) and soft copies.
Please ensure that the invoice is issued correctly by supplier according to the attached sample. Additionally, please review the contract and invoice together.
Please check the PO and make the remaining payment if necessary. Additionally, please inform the accounting department about the payment with the PO number.
Please check the invoice of the exchange rate difference according to the payments made. If necessary, obtain approval from the PD to close the process accounting-wise by offsetting the payment or exchange difference invoices.
Please make final checks of the entire process and obtain confirmation from the PD that the work has been completed.

## CB
Task Name | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
CB INSTRUCTIONS
Please define the service procurement, enter the relevant date and assign a PM for this procurement. You must also give CB warning.
Please use the attached pre-prepared administrative specification as a template and update it accordingly. In addition, please prepare a technical specification for this purchase and attach it to your updated administrative specification.
Please prepare and update proposal request form. Request and gather proposals from suppliers. Archive proposals and proformas digitally.
Please check the digital archive. Submit the proposal comparison chart to PD for approval.
Please use the attached pre-prepared contract as a template and update the yellow highlighted sections accordingly.
Please review the contents of the contract and assign Project Purchasement (PO) number. Have the supplier sign on the contract and Health and Safety Executive (HSE) specification, submit it to PD for approval.
Please specify delivery of work time.
Please review the contract. Pay in advance. If necessary, add to the checklist. In addition, please inform the accounting department about the advance payment with the PO number. Upload the advance payment receipt to this row.
Please add the purchase and purchase schedule to PO list.
Please evaluate the neccessity of the FAT and also please evaluate whether the customer needed in the FAT.
Please ensure that all test documents, material identification and certificates are obtained and archived from the manufacturer, whether FAT has been done or not.
Once the product is ready, please organize the delivery. Prepare a dispatch list and photos of the delivery. If necessary, request the second payment from PD.
Please check the HSE documents provided by the supplier for the HSE contract before starting work on site. Request on-site job training forms from the supplier. If the supplier does not have a form, please have the supplier sign on the our on-site job training form. If all documents and progress are in order, please approve the starting works on site. If there are any outstanding issues, please do not allow work to begin and halt on-site operations.
This is essential that documents be requested from PM before starting the site works. If documents are not provided by PM, please inform PD via text message. Please upload the documents in a folder as hard and soft copies.
Please inspect the site installation works in terms of technical aspects and enforce the service supplier to apply the waste disposal rules and forms on site.
Please require the waste disposal forms from the PM at completion of works.
Please fill and sign Site Acceptance Test (SAT) form and have the supplier sign on the SAT.
Please check all documents recieved from SM. Please also archive all documents as hard(wet ink) and soft copies.
Please ensure that all documents above have been archived as hard (wet ink) and soft copies.
Please ensure that the invoice is issued correctly by supplier according to the attached sample. Additionally, please review the PO and invoice together.
Please check the PO and make the remaining payment if necessary. Additionally, please inform the accounting department about the payment with the PO number.
Please check the invoice of the exchange rate difference according to the payments made. If necessary, obtain approval from the PD to close the process accounting-wise by offsetting the payment or exchange difference invoices.
Please make final checks of the entire process and obtain confirmation from the PD that the work has been completed.

## CS
Task Name | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
CS INSTRUCTIONS
Please define the service procurement, enter the relevant date and assign a PM for this procurement.
Please prepare and update proposal request form. Request and gather proposals from suppliers. Archive proposals and proformas digitally.
Please check the digital archive. Submit the proposal comparison chart to PD for approval.
Please prepare a Project Purchasement (PO) or a contract.
Please review the contents of the contract and assign Project Purchasement (PO) number. Have the supplier sign on the contract and Health and Safety Executive (HSE) specification, submit it to PD for approval.
Please specify delivery of work time.
Please review the PO. Pay in advance. If necessary, add to the checklist. In addition, please inform the accounting department about the advance payment with the PO number. Upload the advance payment receipt to this row.
Please add the purchase and purchase schedule to PO list.
Please evaluate the neccessity of the FAT and also please evaluate whether the customer needed in the FAT.
Please ensure that all test documents, material identification and certificates are obtained and archived from the manufacturer, whether FAT has been done or not.
Once the product is ready, please organize the delivery. Prepare a dispatch list and photos of the delivery. If necessary, request the second payment from PD.
Please check the HSE documents provided by the supplier for the HSE contract before starting work on site. Request on-site job training forms from the supplier. If the supplier does not have a form, please have the supplier sign on the our on-site job training form. If all documents and progress are in order, please approve the starting works on site. If there are any outstanding issues, please do not allow work to begin and halt on-site operations.
This is essential that documents be requested from PM before starting the site works. If documents are not provided by PM, please inform PD via text message. Please upload the documents in a folder as hard and soft copies.
Please inspect the site installation works in terms of technical aspects and enforce the service supplier to apply the waste disposal rules and forms on site.
Please require the waste disposal forms from the PM at completion of works.
Please fill and sign Site Acceptance Test (SAT) form and have the supplier sign on the SAT.
Please check all documents recieved from SM. Please also archive all documents as hard(wet ink) and soft copies.
Please ensure that all documents above have been archived as hard (wet ink) and soft copies.
Please ensure that the invoice is issued correctly by supplier according to the attached sample. Additionally, please review the PO and invoice together.
Please check the PO and make the remaining payment if necessary. Additionally, please inform the accounting department about the payment with the PO number.
Please check the invoice of the exchange rate difference according to the payments made. If necessary, obtain approval from the PD to close the process accounting-wise by offsetting the payment or exchange difference invoices.
Please make final checks of the entire process and obtain confirmation from the PD that the work has been completed.

## SL
Task Name | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
SL INSTRUCTIONS
Please define the service procurement, enter the relevant date and assign a PM for this procurement.
Please prepare and update proposal request form. Request and gather proposals from suppliers. Archive proposals and proformas digitally.
Please check the digital archive. Submit the proposal comparison chart to PD for approval.
Please prepare a Project Purchasement (PO) or a contract.
Please review the contents of the contract and assign Project Purchasement (PO) number. Have the supplier sign on the contract and Health and Safety Executive (HSE) specification, submit it to PD for approval.
Please specify delivery of work time.
Please review the contract. Pay in advance. If necessary, add to the checklist. In addition, please inform the accounting department about the advance payment with the PO number. Upload the advance payment receipt to this row.
Please add the purchase and purchase schedule to PO list.
Please check the HSE documents provided by the supplier for the HSE contract before starting work on site. Request on-site job training forms from the supplier. If the supplier does not have a form, please have the supplier sign on the our on-site job training form. If all documents and progress are in order, please approve the starting works on site. If there are any outstanding issues, please do not allow work to begin and halt on-site operations.
This is essential that documents be requested from PM before starting the site works. If documents are not provided by PM, please inform PD via text message. Please upload the documents in a folder as hard and soft copies.
Please inspect the site installation works in terms of technical aspects and enforce the service supplier to apply the waste disposal rules and forms on site.
Please require the waste disposal forms from the PM at completion of works.
Please prepare and have supplier sign work delivery record.
Please compile the work delivery record and attachments into a single .pdf file and create hard and soft copies of the documents in a folder.
Please ensure that all documents above have been archived as hard (wet ink) and soft copies.
Please ensure that the invoice is issued correctly by supplier according to the attached sample. Additionally, please review the PO and invoice together.
Please check the PO and make the remaining payment if necessary. Additionally, please inform the accounting department about the payment with the PO number.
Please check the invoice of the exchange rate difference according to the payments made. If necessary, obtain approval from the PD to close the process accounting-wise by offsetting the payment or exchange difference invoices.
Please make final checks of the entire process and obtain confirmation from the PD that the work has been completed.

## SC
Task Name | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
SC INSTRUCTIONS
Please define the service procurement, enter the relevant date and assign a PM for this procurement.
Please prepare and update proposal request form. Request and gather proposals from suppliers. Archive proposals and proformas digitally.
Please check the digital archive. Submit the proposal comparison chart to PD for approval.
Please prepare a Project Purchasement (PO).
Please review the contents of the PO and assign Project Purchasement (PO) number.
Please have supplier sign on the Health and Safety Risk Analysis and Emergency Action Plans, which must be controlled sites with PO and Erginer Office Health and Safety Risk Analysis. Verify authorized signature. Have supplier sign on the On-Site Job Training Form.
Please submit the PO to PD for approval signature.
Please specify delivery of work time.
Please review the PO. Pay in advance. If necessary, add to the checklist. In addition, please inform the accounting department about the advance payment with the PO number. Upload the advance payment receipt to this row.
Please add the purchase and purchase schedule to PO list.
Please check the PO and make the second payment due if necessary. Please also notify the accounting department about this second advance payment with the Project Purchasement Number (PO No).
Please request the consultant's ISO, TSE and CE documents, as well as their proficiency/accreditation and consent certificates. Please specify and check the consultant personnel's proficiency and training documents. Following that, if necessary, submit a request to the Finance Department for advance payment.
Please request to the consultant for the documents specified by PM.
Please ensure that all documents above have been archived as hard (wet ink) and soft copies.
Please ensure that the invoice is issued correctly by supplier according to the attached sample. Additionally, please review the PO and invoice together.
Please check the PO and make the remaining payment if necessary. Additionally, please inform the accounting department about the payment with the PO number.
Please check the invoice of the exchange rate difference according to the payments made. If necessary, obtain approval from the PD to close the process accounting-wise by offsetting the payment or exchange difference invoices.
Please make final checks of the entire process and obtain confirmation from the PD that the work has been completed.