## DASHBOARD
NO | ITEMS | QTY | Unit | Unit Price | Total Price | Purchasement Date | Delivery Date | Delivery Type | Additional Insurance Requirement | Lojistic Requirement | Notes
1 | PV MODULE & CONNECTOR | [6 empty] | On-site
2 | SOLAR CABLE | [6 empty] | EXW
3 | INVERTER | [6 empty] | CIF
4 | CONSTRUCTION MATERIAL (TRACKER) | [6 empty] | ?
5 | CIVIL&ELECTRICAL WORKS
6 | MV EQUIPMENTS FOR SPP
7 | LV PANELS
8 | CABLES
9 | GRID CONNECTION (TURN-KEY)
10 | FENCES
11 | EARTHING & LIGHTINING EQUIPMENTS
12 | FIRE EXTINGUISHING SYSTEM
13 | LOGERG & GUARDIAN 3.0 & DRON
14 | CCTV (AVAILABLE TO LOGERG)
15 | ELECTRICAL EQUIPMENTS
16 | VILLA (CONTAINERIZED) & SITE DEPOT
17 | LANDSCAPING WORKS
18 | MANAGEMENT EXPENSES
19 | CEMENT, SAND AND OTHER CIVIL GOODS
20 | MAP ENGINEERING
21 | CONSULTANTS (PWC, CUSTOM CONS., PV MODULE INSPECTOR. COMM. SUPERVISOR)
22 | TAXES AND FEES FOR CONSTRUCTION AND CUSTOM DUTIES
24 | ALL RISK INSURANCE
25 | LOGISTICS (REGIONAL COMPANY)
26 | CUSTOMS WAREHOUSE
27 | OTHERS (ADDITIONAL INSURANCE, OTHER SITE NEEDS)

## Definitions
NO | ITEMS | PURCH. TYPE | MADE IN | SUPPLIER | PRODUCER (BRAND) | CUSTOMS REQ. | PA | PM | PD | NOTES
1 | PV MODULE & CONNECTOR | GB | PRC | JINKO | JINKO | YES
2 | SOLAR CABLE | GB | TR | EGE KABLO | EGE KABLO | YES
3 | INVERTER | GB | PRC | HUAWEI | HUAWEI | YES
4 | CONSTRUCTION MATERIAL (TRACKER) | GB | TR OR PRC | SCHLETTER | SCHLETTER | YES
5 | CIVIL&ELECTRICAL WORKS | SL | EU | EASTERN EUROPEAN COMPANIES | EASTERN EUROPEAN COMPANIES | NO
6 | MV EQUIPMENTS FOR SPP | GB | TR | ERGINER | ORMAZABAL, RTS PREFABRIC, ELTAŞ | ? |  |  |  | İHRAÇ KAYITLI ¦ İTALYAN ŞİRKET DE ARAYALIM
7 | LV PANELS | GB | TR | TEKPAN | TEKPAN | YES
8 | CABLES | GS | TR | ÖZNUR (ERGİNER) | ÖZNUR PYRISMIAN(COM. CABLE) | YES |  |  |  | İHRAÇ KAYITLI
9 | GRID CONNECTION (TURN-KEY) | CB | - | ITALIAN COMPANY | ITALIAN COMPANY |  |  |  |  | MV CABLES EXCLUDED ¦ MV SWITCHGEARS INCLUDED ¦ TERNA&ENEL SCADA INCLUDED
10 | FENCES | GS | ITA OR TR | ITALIAN COMPANY | ITALIAN COMPANY
11 | EARTHING & LIGHTINING EQUIPMENTS | GS | TR | ERGINER | RADSAN | YES |  |  |  | İHRAÇ KAYITLI
12 | FIRE EXTINGUISHING SYSTEM | CS | ITA | ITALIAN COMPANY | ITALIAN COMPANY
13 | LOGERG & GUARDIAN 3.0 & DRON | LIST | TR | ERGINER | EU COMPANIES | ? |  |  |  | DIŞ TİCARET UZMANI İLE GÖRÜŞÜLECEK.
14 | CCTV (AVAILABLE TO LOGERG) | CS | TR | ERGINER | ? | ? |  |  |  | DİREKT ALINABİLECEK FİRMALAR ARAŞTIRILACAK.
15 | ELECTRICAL EQUIPMENTS | GS | TR | ITALIAN COMPANY | ITALIAN COMPANY | NO |  |  |  | BAŞLIK, PABUÇ, MAKARON (ETC)
16 | VILLA (CONTAINERIZED) & SITE DEPOT | GB | TR | ERGINER | ERGINER | YES
17 | LANDSCAPING WORKS | CB | ITA | ITALIAN COMPANY | ITALIAN COMPANY | NO
18 | MANAGEMENT EXPENSES | LIST | ITA | SPV | SPV | NO
19 | CEMENT, SAND AND OTHER CIVIL GOODS | GS | ITA | ITALIAN COMPANY | ITALIAN COMPANY | NO
20 | MAP ENGINEERING | SC | ITA | ITALIAN COMPANY | ITALIAN COMPANY | NO
21 | CONSULTANTS (PWC, CUSTOM CONS., PV MODULE INSPECTOR. COMM. SUPERVISOR) | LIST | - | INTERNATIONAL COMPANIES | INTERNATIONAL COMPANIES | NO
22 | TAXES AND FEES FOR CONSTRUCTION AND CUSTOM DUTIES | LIST | ITA | SPV | SPV | NO
24 | ALL RISK INSURANCE | SC | ITA | PWC | - | NO
25 | LOGISTICS (REGIONAL COMPANY) | SL | ITA
26 | INTERNATIONAL LOGISTICS | SL | EU
26 | CUSTOMS WAREHOUSE | SC | ITA
27 | OTHERS (ADDITIONAL INSURANCE, OTHER SITE NEEDS) | LIST | ITA | ITALIAN COMPANY | ITALIAN COMPANY | NO

## Subdefinitions
AFMB: ALIŞ FATURALARI MAL BÜYÜK | GB | GOODS BIG
AFMK: ALIŞ FATURALARI MAL KÜÇÜK | GS | GOODS SMALL
AFYB: ALIŞ FATURALARI YAPIM BÜYÜK | CB | CONSTRUCTION BIG
AFYK: ALIŞ FATURALARI YAPIM KÜÇÜK | CS | CONSTRUCTION SMALL
AFHİ: ALIŞ FATURALARI HİZMET İŞÇİLİK | SL | SERVICE LABOUR
AFHD: ALIŞ FATURALARI HİZMET DANIŞMANLIK | SC | SERVICE CONSULTANCY

## GB
Task Name |  | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
GB DURATION
MAL ALIMINI TANIMLA, İLK TARİHİ GİR VE İLGİLİ İŞ İÇİN PM ATAMASINI YAP VE AFMB UYARISI VER | DEFINING PRODUCT PURCHASE, SPECIFYING START DATE, ASSIGNING PM, GIVING GB ALERT
HAZIR ŞARTNAMEYİ AL VE ÖZEL ŞARTLAR BÖLÜMÜNÜ GÜNCELLE | PREPARING THE ALREADY CREATED REGULATION AND UPDATING SPECIAL TERMS ACCORDING TO PROJECT
TEKLİF TALEP FORMU HAZIRLA VE TEKLİFLERİ ŞARTNAME ONAYLARI İLE TEMİN ET GELEN TEKLİFLERİ VE PROFORMALARI DİJİTAL OLARAK ARŞİVLE | PREPARING PROPOSAL REQUEST FORM AND COLLECTING THE PROPOSALS WITH APPROVED REGULATIONS ARCHIVING PROPOSALS AND PROFORMAS AS DIGITAL
HAZIR SÖZLEŞMEYİ AL, SARI İLE BOYALI KISIMLARI GÜNCELLE VE GEREKLİ İSE AVUKATLA GÖRÜŞÜP İMZAYA HAZIR HALİNİ BURAYA EKLE | PREPARING THE ALREADY CREATED CONTRACT AND UPDATING PLACES THAT PAINTED AS YELLOW ACCORDING TO PROJECT ATTACHING THE CONTRACT AS READY TO SIGN AFTER CONSULT ON THE LAWYER IF REQUIRED
DİJİTAL ARŞİVİ KONTROL ET VE TEKLİF KARŞILAŞTIRMA TABLOSUNU PM DENETİMİNDE MD ONAYINA SUN. | CONTROLLING OF THE DIGITAL ARCHIVE, SUBMITTING COMPARISON CHART TO MD FOR APPROVAL AFTER CHECKING THE DOCUMENTS WITH PM
HAZIR SÖZLEŞMEYİ AL, SARI İLE BOYALI KISIMLARI GÜNCELLE VE GEREKLİ İSE AVUKATLA GÖRÜŞÜP İMZAYA HAZIR HALİNİ BURAYA EKLE | PREPARING THE ALREADY CREATED CONTRACT AND UPDATING PLACES THAT PAINTED AS YELLOW ACCORDING TO PROJECT ATTACHING THE CONTRACT AS READY TO SIGN AFTER CONSULT ON THE LAWYER IF REQUIRED
SÖZLEŞME İÇERİK KONTROLÜ YAP VE PO NO ATAMA + TEDARİKÇİYE İMZALATINCA MD ONAYINA SUN. | CONTROLLING OF THE CONTACT BY MEANS OF CONTENT AND ASSIGNING PO (PURCHASE ORDER), SUBMITTING THE CONTRACT TO MD FOR APPROVAL AFTER HAVING SUPPLIER SIGN ON THE CONTRACT
SÖZLEŞMEYİ İNCELE VE UYGUNSA İMZALA | EXAMINING THE CONTRACT AND SIGNING
SÖZLEŞMEYİ KONTROL ET VE AVANS ÖDEMESİNİ YAP VE GEREKLİ İSE ÇEK LİSTESİNE EKLE. YAPTIĞIN ÖDEMEYİ MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CHECKING THE CONTRACT AND MAKING ADVANCE PAYMENT, ADDING ON THE CHECK-LIST IF REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE ADVANCE PAYMENT WITH THE PO NUMBER
SİPARİŞİ PO LIST'E EKLE | ADDING THE PURCHASEMENT TO PO LIST
MALZEME TESLİME HAZIRDIR BİLDİRİMİNİ AL VE TESLİMATI ORGANİZE ET GEREKLİ İSE İKİNCİ ÖDEMEYİ MD'DEN TALEP ET | AFTER PRODUCTS IS READY ORGANIZING THE DELIVERY, REQUESTING THE SECOND PAYMENTS FROM MD IF REQUIRED
SÖZLEŞMEYİ KONTROL ET VE VARSA İKİNCİ AVANS VEYA KALAN ÖDEMEYİ YAP. YAPTIĞIN ÖDEMEYİ MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CONTROLLING THE CONTRACT, MAKING OTHER ADVANCE OR REMAINED PAYMENT IF REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE PAYMENT WITH THE PO NUMBER
FAT TALEP ET.FAT YAPILMAYACAK İSE TEST DÖKÜMANLARINI VE MALZEMENİN KİMLİĞİ VEYA SERİTİFKASINI İSTE. | REQUESTING FAT (FACTORY ACCEPTANCE TEST). REQUESTING TEST DOCUMENTS, DATA-SHEETS AND CERTIFICATIONS IF FAT IS NOT REQUIRED
FAT GEREKLİLİĞİ VE MÜŞTERİ KATILIMI GEREKLİLİĞİNİ DEĞERLENDİR | EVALUATING REQUIREMENT OF FAT AND REQUIREMENT OF CUSTOMER ATTENDANCY TO THE FAT
TESLİMAT TİPİNE GÖRE: TESLİMAT SONRASI İÇİN SİGORTA İŞLEMLERİNİ KONTROL ET (İNDİRME-YÜKLEME KAPSAMINI UNUTMA) EKSİKSE TAMAMLANMASI İÇİN QPE'YE İLET | CONTROLLING OF INSURANCE OPERATIONS ACCORDING TO DELIVERY TYPE FOR AFTER TRANSPORTING (SCOPE OF LOADING AND UNLOADING IS ESSENTIAL) SENDING TO QPE FOR COMPLETING IF INCOMPLETE
SİGORTA TALEBİNİ KONTROL ET VE MASTER SİGORTA LİSTESİ'Nİ KONTROL ET VE DURUMA GÖRE POLİÇEYE EKLET VEYA YENİ POLİÇE İÇİN İKİ TEKLİF ALIP ONAYA SUN | CONTROLLING OF INSURANCE REQUEST AND MASTER INSURANCE LIST, ADDING TO INSURANCE POLICY IF REQUIRED OR GETTING TWO PROPOSALS FOR NEW INSURANCE POLICY AND SUBMITTING PROPOSALS TO MANAGER FOR APPROVE
MALLARI EKSİKSİZ TESLİM AL. AKSİ DURUMDA ÇÖZÜMÜ İÇİN TEDARİKÇİ VE YÖNETİCİNDEN DESTEK İSTEYEBİLİRSİN. İRSALİYE VE FOTOĞRAF HAZIRLA VE EVRAKLARI BURAYA YÜKLE | RECEIVING PRODUCTS IN FULL, GETTING SUPPORT FROM SUPPLIER OR RELEVANT MANAGER IF REQUIRED, PREPARING WAYBILL AND PHOTOS AND UPLOADING DOCUMENTS IN THIS ROW
PM'DEN GELEN EVRAKLARI İNCELE VE KLASÖRLE (HARD&SOFT) | EXAMINING AND FILING DOCUMENTS (AS HARD AND SOFT) THAT COME FROM PM
SAT VEYA MAL TESLİM TUTANAĞI FORMUNU DOLDUR. İMZALA VE SÖZLEŞMEDE VAR İSE TEDARİKÇİYE İMZALAT | PREPARING SAT(SITE ACCEPTANCE TEST) OR DELIVERY OF WORK RECORD FORM AND SIGNING, HAVING SUPPLIER SIGN ON THE DELIVERY OF WORK RECORD IF THE CONTRACT REQUIRES
PM'DEN GELEN EVRAKLARI DOSYAYA İŞLE VE KLASÖRLE (HARD&SOFT). | EXAMINING AND FILING DOCUMENTS (AS HARD AND SOFT) THAT COME FROM PM
YUKARIDAKİ TÜM EVRAK VE FOTOLARI HARD COPY OLARAK KLASÖRLEDİĞİNİN KONTROLÜNÜ YAP | CONTROLLING THAT ALL PREVIOUNS DOCUMETS AND PHOTOS ARE MADE IN FOLDER AS HARD COPY
SÜREÇ TAKİBİ VE FATURANIN TEDARİKÇİ TARAFINDAN DOĞRU ŞEKİLDE KESİLDİĞİNE EMİN OL | MONITORING THE PROCESS AND ENSURING THAT INVOICE IS CORRECTLY ISSUED BY SUPPLIER
FATURAYI PO'YA GÖRE KONTROL ET VE KABUL ET TARAMA YAP SOFT COPY OLARAK BULUTA KAYDET | CHECKING THE INVOICE IN ACCORDANCE WITH THE PO AND ACCEPTING THE INVOICE, SCANNING THE PO AND UPLOADING TO CLOUD AS SOFT COPY
PO'YU KONTROL ET VE VARSA KALAN ÖDEMEYİ YAP. YAPTIĞIN ÖDEMEYİ VE FATURALARI MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CHECKING THE PO AND MAKING REMAINING PAYMENT IF REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE PAYMENT AND INVOICES WITH THE PO NUMBER
VARSA KALAN ÖDEMEYİ YAP, YAPILAN ÖDEMELERE GÖRE KUR FARKI FATURASI KONTROLÜNÜ YAP ve MD'DEN ONAY AL | MAKING REMAINING PAYMENT IF REQUIRED, CHECKING EXCHANGE DIFFERENCE INVOICE IN ACCORDANCE WITH PAYMENTS AND RECEIVING APPROVAL FROM MD
SON KONTROLLERİ YAP VE İŞİN TAMAMLANDIĞINA DAİR MD'DEN ONAY AL | MAKING LAST CONTROLLS, RECEIVING APPROVAL RELATED TO COMPLETING THE WORKS FROM MD
+++++++++++++++++++++

## GS
Task Name |  | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
GS DURATION | [13 empty] | 0%
MAL ALIMINI TANIMLA, İLK TARİHİ GİR VE İLGİLİ İŞ İÇİN PM ATAMASINI YAP VE AFMK UYARISI VER | DEFINING PRODUCT PURCHASE, SPECIFYING START DATE, ASSIGNING PM, GIVING GS ALERT
TEKLİF TALEP FORMU HAZIRLA GELEN TEKLİFLERİ VE PROFORMALARI DİJİTAL OLARAK ARŞİVLE | PREPARING PROPOSAL REQUEST FORM, ARCHIVING PROPOSALS AND PROFORMAS AS DIGITAL
DİJİTAL ARŞİVİ KONTROL ET VE TEKLİF KARŞILAŞTIRMA TABLOSUNU PM DENETİMİNDE MD ONAYINA SUN. | CONTROLLING OF THE DIGITAL ARCHIVE, SUBMITTING COMPARISON CHART TO MD FOR APPROVAL AFTER CHECKING THE DOCUMENTS WITH PM
PO (SİPARİŞ EMRİ) HAZIRLA PO'YU VE ONAYLI FORMU QPE'YE TESLİM ET | PREPARING PO (PURCHASE ORDER), DELIVERING THE PO AND APPROVED FORM TO QPE
PO (SİP. EMRİ) İÇERİK KONT. YAP PO ve PROJE NO ATA PO'YU TEDARİKÇİYE İMZALAT VE MD'NİN ONAYINA SUN | CHECKING THE PO IN TERMS OF SUBSTANCE, ASSIGNING THE PO NUMBER AND PROJECT NUMBER, HAVING SUPPLIER SIGN ON THE PO, SUBMITTING THE PO TO MD FOR APPROVE
PO'YU KONTROL ET VE AVANS ÖDEMESİNİ YAP VE GEREKLİ İSE ÇEK LİSTESİNE EKLE. YAPTIĞIN ÖDEMEYİ MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CHECKING THE PO, MAKING ADVANCE PAYMENT AND ATTACHING CHECK LIST IF IS REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE ADVANCE PAYMENT WITH THE PO NUMBER
SİPARİŞİ PO LIST'E EKLE | ADDING THE PURCHASEMENT TO PO LIST
MALZEME TESLİME HAZIRDIR BİLDİRİMİNİ AL VE TESLİMATI ORGANİZE ET GEREKLİ İSE İKİNCİ ÖDEMEYİ MD'DEN TALEP ET | AFTER PRODUCTS IS READY ORGANIZING THE DELIVERY, REQUESTING THE SECOND PAYMENTS FROM MD IF REQUIRED
SÖZLEŞMEYİ KONTROL ET VE VARSA İKİNCİ AVANS VEYA KALAN ÖDEMEYİ YAP. YAPTIĞIN ÖDEMEYİ MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CONTROLLING THE CONTRACT, MAKING OTHER ADVANCE OR REMAINED PAYMENT IF REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE PAYMENT WITH THE PO NUMBER
MALLARI EKSİKSİZ TESLİM AL. AKSİ DURUMDA ÇÖZÜMÜ İÇİN TEDARİKÇİ VE YÖNETİCİNDEN DESTEK İSTEYEBİLİRSİN. İRSALİYE VE FOTOĞRAF HAZIRLA VE EVRAKLARI BURAYA YÜKLE | RECEIVING PRODUCTS IN FULL, GETTING SUPPORT FROM SUPPLIER OR RELEVANT MANAGER IF REQUIRED, PREPARING WAYBILL AND PHOTOS AND UPLOADING DOCUMENTS IN THIS ROW
PM'DEN GELEN EVRAKLARI İNCELE VE KLASÖRLE (HARD&SOFT) | EXAMINING AND FILING DOCUMENTS (AS HARD AND SOFT) THAT COME FROM PM
SÜREÇ TAKİBİ VE FATURANIN TEDARİKÇİ TARAFINDAN DOĞRU ŞEKİLDE KESİLDİĞİNE EMİN OL | MONITORING THE PROCESS AND ENSURING THAT INVOICE IS CORRECTLY ISSUED BY SUPPLIER
FATURAYI PO'YA GÖRE KONTROL ET VE KABUL ET TARAMA YAP SOFT COPY OLARAK BULUTA KAYDET | CHECKING THE INVOICE IN ACCORDANCE WITH THE PO AND ACCEPTING THE INVOICE, SCANNING THE PO AND UPLOADING TO CLOUD AS SOFT COPY
PO'YU KONTROL ET VE VARSA KALAN ÖDEMEYİ YAP. YAPTIĞIN ÖDEMEYİ VE FATURALARI MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CHECKING THE PO AND MAKING REMAINING PAYMENT IF REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE PAYMENT AND INVOICES WITH THE PO NUMBER
VARSA KALAN ÖDEMEYİ YAP, YAPILAN ÖDEMELERE GÖRE KUR FARKI FATURASI KONTROLÜNÜ YAP ve MD'DEN ONAY AL | MAKING REMAINING PAYMENT IF REQUIRED, CHECKING EXCHANGE DIFFERENCE INVOICE IN ACCORDANCE WITH PAYMENTS AND RECEIVING APPROVAL FROM MD
SON KONTROLLERİ YAP VE İŞİN TAMAMLANDIĞINA DAİR MD'DEN ONAY AL | MAKING LAST CONTROLLS, RECEIVING APPROVAL RELATED TO COMPLETING THE WORKS FROM MD

## CB
Task Name |  | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
CB DURATION
HİZMET ALIMINI TANIMLA, İLK TARİHİ GİR VE İLGİLİ İŞ İÇİN PM ATAMASINI YAP | DEFINING SERVICE PURCHASE, SPECIFYING START DATE, ASSIGNING PM,
HAZIR ŞARTNAMEYİ AL VE ÖZEL ŞARTLAR BÖLÜMÜNÜ GÜNCELLE | PREPARING THE ALREADY CREATED REGULATION AND UPDATING SPECIAL TERMS ACCORDING TO PROJECT
EKİBİNE BFÇ HAZIRLAT VE DENETLE | BFÇ?
TEKLİF TALEP FORMU HAZIRLA GELEN TEKLİFLERİ VE PROFORMALARI DİJİTAL OLARAK ARŞİVLE | PREPARING PROPOSAL REQUEST FORM, ARCHIVING PROPOSALS AND PROFORMAS AS DIGITAL
DİJİTAL ARŞİVİ KONTROL ET VE TEKLİF KARŞILAŞTIRMA TABLOSUNU PM DENETİMİNDE MD ONAYINA SUN. | CONTROLLING OF THE DIGITAL ARCHIVE, SUBMITTING COMPARISON CHART TO MD FOR APPROVAL AFTER CHECKING THE DOCUMENTS WITH PM
HAZIR SÖZLEŞMEYİ AL VE SARI İLE BOYALI KISIMLARI GÜNCELLE | PREPARING THE ALREADY CREATED CONTRACT AND UPDATING PLACES THAT PAINTED AS YELLOW ACCORDING TO PROJECT
SÖZLEŞME İÇERİK KONT. PO NO ATA SÖZ. VE İSG ŞART.Nİ BELGEMİZİ TEDARİKÇİYE İMZALAT MD ONAYINA SUN | CONTROLLING OF THE CONTACT BY MEANS OF THE CONTENT AND ASSIGNING PO (PURCHASE ORDER), HAVING SUPPLIER SIGN ON THE CONTRACT AND HSE (HEALTH AND SAFETY EXECUTIVE), SUBMITING THE CONTRACT AND HSE TO MD FOR APPROVAL
İŞ TESLİM SÜRESİ | DELIVERY OF WORK TIME
SÖZLEŞMEYİ KONTROL ET VE AVANS ÖDEMESİNİ YAP VE GEREKLİ İSE ÇEK LİSTESİNE EKLE. YAPTIĞIN ÖDEMEYİ MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR. DEKONTU BURAYA YÜKLE | CHECKING THE CONTRACT AND MAKING ADVANCE PAYMENT, ADDING ON THE CHECK-LIST IF REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE ADVANCE PAYMENT AND THE PO NUMBER UPLOADING THE ADVANCE PAYMENT RECEIPT TO THIS ROW
SİPARİŞİ VE ÖDEME TAKVİMİNİ PO LIST'E EKLE | ADDING THE PURCHASEMENT AND PURCHASEMENT SCHEDULE TO PO LIST
FAT GEREKLİLİĞİ VE MÜŞTERİ KATILIMI GEREKLİLİĞİNİ DEĞERLENDİR | EVALUATING REQUIREMENT OF FAT AND REQUIREMENT OF CUSTOMER ATTENDANCY TO THE FAT
MD'DEN ONAY ALARAK FAT TALEP ET.FAT YAPILMAYACAK İSE TEST DÖKÜMANLARINI VE MALZEMENİN KİMLİĞİ VEYA SERİTİFKASINI İSTE. GEREKLİ İSE MÜŞTERİYİ DE DAVET ET. FAT BELGESİ İÇİN TEDARİKÇİNİN FORMU KULLANILACAK/YOKSA TEST DÖKÜMANI KARŞILIKLI İMZALANACAK. | REQUESTING FAT (FACTORY ACCEPTANCE TEST) AFTER MD APPROVAL, REQUESTING TEST DOCUMENTS, DATA-SHEETS AND CERTIFICATIONS IF FAT IS NOT REQUIRED, SUPPLIER'S FAT FORM MUST BE USED. IF SUPPLIER DOESN'T HAVE THE ANY FAT FORM, FAT FORM MUST BE CREATED AND SIGNED MUTUALLY
MALZEME HAZIRDIR BİLDİRİMİNİ PO'DAKİ VEYA SÖZLEŞMEDEKİ NAKLİYE SORUMLULUĞUNU KONTROL ET TEDARİKÇİ İLE GÖRÜŞÜP SİGORTALARI DA KONTROL EDEREK NAKLİYEYİ ORGANİZE ET | CONTROLLING READINESS OF THE PRODUCTS, CONTROLLING STATEMENTS OF TRANSPORTATION ON THE PO OR CONTRACT, ORGANISING THE TRANSPORTATION AFTER CHECKING TRANSPORTATION STATEMENTS OF THE INSURANCE
MALZEME SAHA TESLİMİ İRSALİYE VE FOTOĞRAF HAZIRLA VE EVRAKLARI QPE'YE İLET | ORGANISING PRODUCTS DELIVERY TO SITE
İŞÇİLİK/MONTAJ İÇİN SAHAYA GİTMEDEN EVVEL "İSG ŞARTNAMESİ" İÇİN GÖNDERİLEN EVRAKLARI KONTROL ET. İŞ BAŞI EĞİTİM FORMLARINI TALEP ET (TEDARİKÇİDEN) EĞER YOKSA TEDARİKÇİYE BİZİM FORMU İMZALAT. İŞ BAŞI EĞİTİM FORMU (İMZALI) HERŞEY UYGUN İSE İŞE BAŞLAMA ONAYINI VER. İŞE BAŞLAMA ONAYI (İMZALI) UYGUN DEĞİL İSE İŞİ BAŞLATMAMA VEYA DURDURMA İLE İLGİLİ TÜM YETKİ VE SORUMLULUK SENDE. | CHECKING HSE DOCUMENTS THAT COME FROM THE SUPPLIER FOR HSE CONTRACT BEFORE STARTING SITE WORKS, REQUESTING ON-SITE-JOB TRAINING FORMS FROM THE SUPPLIER, IF THE SUPPLIER DOESNT HAVE A FORM, HAVING SUPPLIER SIGN ON THE OUR ON-SITE-JOB TRAINING FORM (SIGNED), IF ALL DOCUMENTS AND PROGRESS ARE PROPER, APPROVING THE STARTING WORKS, IF NOT, DONT ALLOVING THE START, CEASING THE SITE WORKS
PM'DEN EVRAKLARI İSTE VE TAKİP ET SAHAYA GİRİLMEDEN EVVEL MUTLAKA AL. EĞER GELMEZ İSE MD'YE YAZILI OLARAK BİLDİR. DOSYAYA İŞLE VE KLASÖRLE (HARD&SOFT). | ASKING THE DOCUMENTS FROM THE PM BEFORE STARTING THE SITE WORKS, THIS IS ESSENTIAL. IF DOCUMENTS ARE NOT CAME FROM PM, INFORMING THE MD BY TEXT MAKING DOCUMENTS FILE IN A FOLDER AS HARD&SOFT
İŞÇİLİK/MONTAJ SIRASINDA SAHADA GEREKLİ TEKNİK KONTROLLERİ YAP ATIK KABUL FORMLARINI TEDARİKÇİYE UYGULAT | INSPECTING SITE INSTALLATION WORKS IN TERMS OF TECNICALLY, ENFORCING WASTE DISPOSAL RULES AND FORMS ON THE SITE
İŞ BİTİMİNDE ATIK KABUL FORMLARINI PM'DEN TEMİN ET. | ASKING THE WASTE DISPOSAL FORMS FROM THE PM AT COMPLETION OF WORKS
SAT FORMUNU DOLDUR. İMZALA VE TEDARİKÇİYE İMZALAT | FILLING, SIGNING AND HAVING SUPPLIER SIGN ON THE SAT (SITE ACCEPTANCE TEST) FORM
PM'DEN GELEN EVRAKLARI DOSYAYA İŞLE VE KLASÖRLE (HARD&SOFT). | EXAMINING AND FILING DOCUMENTS (AS HARD AND SOFT) THAT COME FROM PM
YUKARIDAKİ TÜM EVRAK VE FOTOLARI HARD COPY OLARAK KLASÖRLEDİĞİNİN KONTROLÜNÜ YAP | CONTROLLING THAT ALL PREVIOUNS DOCUMETS AND PHOTOS ARE MADE IN FOLDER AS HARD COPY
SÜREÇ TAKİBİ VE FATURANIN TEDARİKÇİ TARAFINDAN DOĞRU ŞEKİLDE KESİLDİĞİNE EMİN OL | MONITORING THE PROCESS AND ENSURING THAT INVOICE IS CORRECTLY ISSUED BY SUPPLIER
FATURAYI PO'YA GÖRE KONTROL ET VE KABUL ET TARAMA YAP SOFT COPY OLARAK BULUTA KAYDET VE VARSA KALAN ÖDEMEYİ YAP. YAPTIĞIN ÖDEMEYİ VE FATURALARI MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CHECKING THE INVOICE IN ACCORDANCE WITH THE PO AND ACCEPTING THE INVOICE, SCANNING THE PO AND UPLOADING TO CLOUD AS SOFT COPY
YAPILAN ÖDEMELERE GÖRE KUR FARKI FATURASI KONTROLÜNÜ YAP ve MD'DEN ONAY AL | CHECKING EXCHANGE DIFFERENCE INVOICE IN ACCORDANCE WITH PAYMENTS AND RECEIVING APPROVAL FROM MD
SON KONTROLLERİ YAP VE İŞİN TAMAMLANDIĞINA DAİR MD'DEN ONAY AL | MAKING LAST CONTROLLS, RECEIVING APPROVAL RELATED TO COMPLETING THE WORKS FROM MD

## SL
Task Name |  | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
SL DURATION
HİZMET ALIMINI TANIMLA, İLK TARİHİ GİR VE İLGİLİ İŞ İÇİN PM ATAMASINI YAP | DEFINING SERVICE PURCHASE, SPECIFYING START DATE, ASSIGNING PM
TEKLİF TALEP FORMU HAZIRLA GELEN TEKLİFLERİ VE PROFORMALARI DİJİTAL OLARAK ARŞİVLE | PREPARING PROPOSAL REQUEST FORM, ARCHIVING OFFERS AND PROFORMAS AS DIGITAL,
DİJİTAL ARŞİVİ KONTROL ET VE TEKLİF KARŞILAŞTIRMA TABLOSUNU PM DENETİMİNDE MD ONAYINA SUN. | CONTROLLING OF DIGITAL ARCHIVE, SUBMITTING COMPARISON CHART TO MD FOR APPROVAL AFTER CHECKING THE DOCUMENTS WITH PM
PO veya SÖZLEŞME HAZIRLA | PREPARING PO (PURCHASE ORDER) OR CONTRACT
PO İÇERİK KONTROLÜ PO NO ATA PO VE "İSG ŞARTNAMESİ" BELGEMİZİ TEDARİKÇİYE İMZALAT | CHECKING THE PO IN TERMS OF SUBSTANCE, ASSIGNING THE PO NUMBER AND PROJECT NUMBER, HAVING SUPPLIER SIGN ON THE PO AND HSE (HEALTH AND SAFETY EXECUTIVE),
UYGUNSA PO VEYA SÖZLEŞME İMZALANACAK MD ONAYINA SUN. | SUBMITTING AND SIGNING THE PO OR CONTRACT TO MD FOR APPROVAL
İŞ TESLİM SÜRESİ | DELIVERY OF WORK TIME
SÖZLEŞMEYİ KONTROL ET VE AVANS ÖDEMESİNİ YAP VE GEREKLİ İSE ÇEK LİSTESİNE EKLE. YAPTIĞIN ÖDEMEYİ MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR. DEKONTU BURAYA YÜKLE | CHECKING THE PO OR CONTRACT, MAKING ADVANCE PAYMENT AND ATTACHING CHECK LIST IF IS REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE ADVANCE PAYMENT WITH THE PO NUMBER UPLOADING THE PAYMENT RECEIPT TO THIS ROW
SİPARİŞİ VE ÖDEME TAKVİMİNİ PO LIST'E EKLE | ATTACHING THE PURCHASE AND THE PAYMENT SCHEDULE TO THE PO LIST
İŞÇİLİK/MONTAJ İÇİN SAHAYA GİTMEDEN EVVEL "İSG ŞARTNAMESİ" İÇİN GÖNDERİLEN EVRAKLARI KONTROL ET. İŞ BAŞI EĞİTİM FORMLARINI TALEP ET (TEDARİKÇİDEN) EĞER YOKSA TEDARİKÇİYE BİZİM FORMU İMZALAT. İŞ BAŞI EĞİTİM FORMU (İMZALI) HERŞEY UYGUN İSE İŞE BAŞLAMA ONAYINI VER. İŞE BAŞLAMA ONAYI (İMZALI) UYGUN DEĞİL İSE İŞİ BAŞLATMAMA VEYA DURDURMA İLE İLGİLİ TÜM YETKİ VE SORUMLULUK SENDE. | CHECKING HSE DOCUMENTS THAT COME FROM SERVICE&WORKMANSHIP SUPPLIER FOR HSE CONTRACT BEFORE STARTING SITE WORKS, REQUESTING ON-SITE-JOB TRAINING FORMS FROM THE SERVICE&WORKMANSHIP SUPPLIER, IF THE SUPPLIER DOESNT HAVE A FORM, HAVING SUPPLIER SIGN ON THE OUR ON-SITE-JOB TRAINING FORM (SIGNED), IF ALL DOCUMENTS AND PROGRESS ARE PROPER, APPROVING THE STARTING WORKS, IF NOT, DONT ALLOVING THE START, CEASING THE SITE WORKS
PM'DEN EVRAKLARI İSTE VE TAKİP ET SAHAYA GİRİLMEDEN EVVEL MUTLAKA AL. EĞER GELMEZ İSE MD'YE YAZILI OLARAK BİLDİR. DOSYAYA İŞLE VE KLASÖRLE (HARD&SOFT). | ASKING THE DOCUMENTS FROM THE PM BEFORE STARTING THE SITE WORKS, THIS IS ESSENTIAL. IF DOCUMENTS ARE NOT CAME FROM PM, INFORMING THE MD BY TEXT MAKING DOCUMENTS FILE IN A FOLDER AS HARD&SOFT
İŞÇİLİK/MONTAJ SIRASINDA SAHADA GEREKLİ TEKNİK KONTROLLERİ YAP ATIK KABUL FORMLARINI TEDARİKÇİYE UYGULAT | INSPECTING SITE INSTALLATION WORKS IN TERMS OF TECNICALLY, ENFORCING WASTE DISPOSAL RULES AND FORMS ON THE SITE
İŞ BİTİMİNDE ATIK KABUL FORMLARINI PM'DEN TEMİN ET. | ASKING THE WASTE DISPOSAL FORMS FROM THE PM AT COMPLETION OF WORKS
İŞ TESLİM TUTANAĞI (KABUL) | WORK DELIVERY RECORD (ACCEPTING)
GELEN İŞ TESLİM TUTANAĞI VE EKLERİNİ TEK BİR .PDF OLARAK DÜZENLE VE SOFT HARD COPY OLARAK KLASÖRLE | ARRANGING THE WORK DELIVERY RECORD AND ATTACHMENTS IN ONLY ONE .pdf FILE, MAKING DOCUMENTS FILE IN A FOLDER AS HARD&SOFT
YUKARIDAKİ TÜM EVRAK VE FOTOLARI HARD COPY OLARAK KLASÖRLEDİĞİNİN KONTROLÜNÜ YAP | CONTROLLING THAT ALL PREVIOUNS DOCUMETS AND PHOTOS ARE MADE IN FOLDER AS HARD COPY
SÜREÇ TAKİBİ VE FATURANIN TEDARİKÇİ TARAFINDAN DOĞRU ŞEKİLDE KESİLDİĞİNE EMİN OL | MONITORING THE PROCESS AND ENSURING THAT INVOICES ARE CORRECTLY CREATED BY THE SUPPLIER
FATURAYI PO'YA GÖRE KONTROL ET VE KABUL ET TARAMA YAP SOFT COPY OLARAK BULUTA KAYDET VE VARSA KALAN ÖDEMEYİ YAP. YAPTIĞIN ÖDEMEYİ VE FATURALARI MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CHECKING AND ACCEPTING THE INVOICE ACCORDING TO PO SCANNING THE DOCUMENTS UPLOADING THE INVOICE AS SOFT COPY, MAKING PAYMENT IF THERE IS ANY REMAINING PAYMENT. INFORMING ACCOUNTING DEPARTMENT ABOUT THE PAYMENT AND INVOICES WITH THE PO NUMBER
VARSA KALAN ÖDEMEYİ YAP, YAPILAN ÖDEMELERE GÖRE KUR FARKI FATURASI KONTROLÜNÜ YAP ve MD'DEN ONAY AL | MAKING REMAINING PAYMENT IF REQUIRED, CHECKING EXCHANGE DIFFERENCE INVOICE IN ACCORDANCE WITH PAYMENTS AND RECEIVING APPROVAL FROM MD
SON KONTROLLERİ YAP VE İŞİN TAMAMLANDIĞINA DAİR MD'DEN ONAY AL | MAKING LAST CONTROLLS, RECEIVING APPROVAL RELATED TO COMPLETING THE WORKS FROM MD

## SC
Task Name |  | Duration | Start | Finish | Tittle | Assigned To | Progress | Progress Comments | Status | Complete Date | MD Approval Status | Notes | Predecessors | % Complete | Next Assigned | Supplier | Tedarikçi No | PO NO
SC DURATION
HİZMET ALIMINI TANIMLA, İLK TARİHİ GİR VE İLGİLİ İŞ İÇİN PM ATAMASINI YAP | DEFINING SERVICE PURCHASE, SPECIFYING START DATE, ASSIGNING PM
TEKLİF TALEP FORMU HAZIRLA GELEN TEKLİFLERİ VE PROFORMALARI QPE'YE İLET | PREPARING PROPOSAL REQUEST FORM, ARCHIVING OFFERS AND PROFORMAS AS DIGITAL,
DİJİTAL ARŞİVİ KONTROL ET VE TEKLİF KARŞILAŞTIRMA TABLOSUNU PM DENETİMİNDE MD ONAYINA SUN. | CONTROLLING OF DIGITAL ARCHIVE, SUBMITTING COMPARISON CHART TO MD FOR APPROVAL AFTER CHECKING THE DOCUMENTS WITH PM
PO HAZIRLA | PREPARING PO (PURCHASE ORDER)
PO İÇERİK KONTROLÜ PO NO ATA | CHECKING THE PO IN TERMS OF SUBSTANCE, ASSIGNING THE PO NUMBER AND PROJECT NUMBER,
PO VE ERGİNER OFİS İSG RİSK ANALİZİ İLE BERABER ZİYARETİ YAPILACAK SAHALARIN İSG RİSK ANALİZLERİNİ ve ACİL DURUM EYLEM PLANLARINI TEDARİKÇİYE İMZALAT (YETKİLİ İMZA KONTROLÜ YAP) VE İŞBAŞI EĞİTİM FORMUNU İMZALAT | HAVING SUPPLIER SIGN ON THE HSE (HEALTH AND SAFETY EXECUTIVE) RISK ANALYSIS AND EMERGENCY ACTION PLAN WITH ERGINER OFFICE HSE RISK ANALYSIS, CHECKING AUTHORIZED SIGNATURE, HAVING SUPPLIER SIGN ON THE ON-SITE-JOB TRAINING FORM,
UYGUNSA PO VEYA SÖZLEŞME İMZALANACAK MD ONAYINA SUN. | SUBMITTING AND SIGNING THE PO OR CONTRACT TO MD FOR APPROVAL
İŞ TESLİM SÜRESİ | DELIVERY OF WORK TIME
PO'YU KONTROL ET VE AVANS ÖDEMESİNİ YAP VE GEREKLİ İSE ÇEK LİSTESİNE EKLE. YAPTIĞIN ÖDEMEYİ MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CHECKING THE PO, MAKING ADVANCE PAYMENT AND ATTACHING CHECK LIST IF IS REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE ADVANCE PAYMENT WITH THE PO NUMBER
SİPARİŞİ VE ÖDEME TAKVİMİNİ PO LIST'E EKLE | ATTACHING THE PURCHASE AND THE PAYMENT SCHEDULE TO THE PO LIST
PO'YU VEYA SÖZLEŞMEYİ KONTROL ET VE VARSA İKİNCİ AVANS VEYA KALAN ÖDEMEYİ YAP. YAPTIĞIN ÖDEMEYİ MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CONTROLLING THE PO OR THE CONTRACT, MAKING OTHER ADVANCE OR REMAINED PAYMENT IF REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE PAYMENT WITH THE PO NUMBER
FİRMANIN ISO, TSE VE CE BELGELERİNİ, YETKİNLİK / AKREDİTASYON VE İZİN BELGELERİNİ İSTE. HİZMET VERECEK PERSONELİN YETKİNLİK VE EĞİTİM BELGELERİNİ BELİRLE VE QPE'YE İLET VE GELENLERİ KONTROL ET. SONRASINDA AVANS ÖDEMESİ VAR İSE FİNANSTAN TALEP ET. | REQUESTING CONSULTANT'S ISO, TSE AND CE DOCUMENTS, ALSO PROFICIENCY / ACCREDITATION AND CONSENT CERTIFICATES, SPECIFIYING PROFICIENCY AND TRAINING DOCUMENTS AND SENDING SENDING TO QPE, CHECKING DOCUMENTS THAT COME FROM THE CONSULTANT, AFTER THAT, REQUESTING ADVANCE PAYMENT FROM FINANCE DEPARTMENT IF REQUIRED
PM'İN BELİRLEDİĞİ EVRAKLARI TALEP ET. YUKARIDAKİ TÜM EVRAKLARI HARD VE SOFT COPY OLARAK KLASÖRLE. | REQUESTING DOCUMENTS THAT SPECIFIED BY PM,
YUKARIDAKİ TÜM EVRAK VE FOTOLARI HARD COPY OLARAK KLASÖRLEDİĞİNİN KONTROLÜNÜ YAP | CONTROLLING THAT ALL PREVIOUNS DOCUMETS AND PHOTOS ARE MADE IN FOLDER AS HARD COPY
SÜREÇ TAKİBİ VE FATURANIN TEDARİKÇİ TARAFINDAN DOĞRU ŞEKİLDE KESİLDİĞİNE EMİN OL | MONITORING THE PROCESS AND ENSURING THAT INVOICE IS CORRECTLY ISSUED BY SUPPLIER
FATURAYI PO'YA GÖRE KONTROL ET VE KABUL ET TARAMA YAP SOFT COPY OLARAK BULUTA KAYDET | CHECKING THE INVOICE IN ACCORDANCE WITH THE PO AND ACCEPTING THE INVOICE, SCANNING THE PO AND UPLOADING TO CLOUD AS SOFT COPY
PO'YU KONTROL ET VE VARSA KALAN ÖDEMEYİ YAP. YAPTIĞIN ÖDEMEYİ VE FATURALARI MUHASEBEYE PO NO İLE BİRLİKTE BİLDİR | CHECKING THE PO AND MAKING REMAINING PAYMENT IF REQUIRED, INFORMING ACCOUNTING DEPARTMENT ABOUT THE PAYMENT AND INVOICES WITH THE PO NUMBER
VARSA KALAN ÖDEMEYİ YAP, YAPILAN ÖDEMELERE GÖRE KUR FARKI FATURASI KONTROLÜNÜ YAP ve MD'DEN ONAY AL | MAKING REMAINING PAYMENT IF REQUIRED, CHECKING EXCHANGE DIFFERENCE INVOICE IN ACCORDANCE WITH PAYMENTS AND RECEIVING APPROVAL FROM MD
SON KONTROLLERİ YAP VE İŞİN TAMAMLANDIĞINA DAİR MD'DEN ONAY AL | MAKING LAST CONTROLLS, RECEIVING APPROVAL RELATED TO COMPLETING THE WORKS FROM MD